## Slide 1: What Makes a CFI Proposal or Award so “Special”? Research Administration Day, May 31, 2017 “Today’s Research, Our Future” Partnership and Institutional Projects, Research Services Office Kara Allanach, Manager Institutional Projects Nancy Klimczak, Assistant Director
RAD 202

## Slide 2: Topics:
Welcome and Introductions
What is the Canada Foundation for Innovation?
Key CFI Guidelines
CFI vs. Typical research proposals
  Budgets: CFI “In-kind” contributions
  Construction/Renovation requirements
  Environmental Scan: Integration with existing infrastructure
Lessons learned from reviewer comments
QUESTIONS

## Slide 3: Who are we? The Institutional Projects Team
Campus Unit | Name | Role | Phone | E-mail
RSO | Nancy Klimczak | Assistant Director, Partnership & Institutional Projects | 780-492-1452 | nancy.klimczak@ualberta.ca
RSO | Kara Allanach | Manager, Institutional Projects | 780-492-8936 | kara.allanach@ualberta.ca
RSO | Gareth Corry | Contracts Specialist | 780-492-8032 | gcorry@ualberta.ca
RSO | Mireille Estephan | Contracts Specialist | 780-492-8378 | mireille.estephan@ualberta.ca
RSO | Liz Huston | Contracts Specialist | 780-492-1430 | liz.huston@ualberta.ca
RSO | Ryan McKenzie | Contracts Specialist | 780-492-6154 | ryan.mckenzie@ualberta.ca
RSO | Gonzalo Vilas | Contracts Specialist | 780-492-2753 | gonzalo.vilas@ualberta.ca
RSO | Vera Harris | Research Support Administrator | 780-492-8566 | vera.harris@ualberta.ca
RSO | Esther Yeung | Research Support Administrator | 780-492-2922 | eyeung@ualberta.ca
RSO | Lisa Cruywels | Research Support Administrator | 780-492-8623 | cruywels@ualberta.ca
RSO | Vanessa Incani | Research Support Administrator | 780-492-2406 | vincani@ualberta.ca
F&O | Asia Szkudlarek | Project Cost Analyst - CFI | 780-492-1166 | aszkudlarek@ualberta.ca

## Slide 4: Who are we? The Institutional Projects Team
The Institutional Projects team is involved with each CFI project throughout its entire lifetime
We provide support for:
      Proposal Development
      Budget Development
      Award Finalization
      Negotiation of Agreements
      Review and Approval of all purchases >$10K
      Reporting
      Project Closure
      Audit Support (if applicable)

## Slide 5: What is CFI?

## Slide 6: Canada Foundation for Innovation
“Allocation” or “Envelope”
Independent corporation, founded in 1997
Receives funding from the Federal Government
CFI’s Mandate:
      To make financial contributions to Canada’s universities, colleges, research hospitals and non-profit research organizations to increase their capacity to carry out high quality research.

## Slide 7: Canada Foundation for Innovation: Objectives
  Increase Canada’s capability to carry out world-class scientific research and technology development
  Support economic growth and job creation, as well as health and environmental quality through innovation
  Expand research and job opportunities by providing support through research infrastructure for the development of highly qualified personnel
  Promote productive networks and collaboration among Canadian institutions and the private sector

## Slide 8: CFI Awards are Institutional Awards
CFI projects are awarded to the institution, rather than to faculty members
      The PI is the Project Leader
      Vice President (Research) is the Project Holder
CFI funds the acquisition of infrastructure, not research
The Institution has a contractual obligation to manage all CFI funds in accordance with CFI policies
      CFI carries out regular audits and monitoring visits
Non-compliance on a single project can result in widespread effects on all institutional CFI funding

## Slide 9: CFI Award Funding Structure
CFI funds maximum 40% of Total Project Costs (TPC)
Request can be made to Ministry of Economic Development and Trade (EDT) for additional 40% of TPC
Remaining 20% to come from other sources:
    Eligible partners
    Vendor in-kind contributions
    Institutional contributions

## Slide 10: Partner Contributions
Eligible Partners:
    Institutional funds
    Most departments/agencies of the federal and provincial governments
    Industry partners (unless already matched)
    Non-profit organizations
    Individuals
Non-eligible Partners:
    CIHR
    NSERC
    SSHRC
    NCE
    CRC
    ***Not an exhaustive list.

## Slide 11: Canada Foundation for Innovation Key Guidelines
Changes to the Infrastructure
  “The CFI funds specific items of an infrastructure project that have been subject to a merit-based review.
  As such, the institution is expected to use CFI funds to purchase the infrastructure items identified in the proposal.”
  --CFI Policy and Program Guide, Sec. 6.6.1
  However,
  Both CFI and the institution recognize that technology continues to develop and changes are sometimes inevitable.
  Therefore:
  **Institutional review is required for all changes**

## Slide 12: Canada Foundation for Innovation Key Guidelines
Eligible Costs:
    Acquisition and installation of infrastructure (including databases)
    Construction and renovation costs required to house the CFI-funded infrastructure
    Operations and maintenance of CFI-funded infrastructure (including HQP salaries)
Ineligible Costs:
    Any cost to conduct research activities
    Trainee stipends or researcher salaries (students, post-doctoral fellows)
    Infrastructure primarily used for teaching or clinical care
    ***this is a non-exhaustive list

## Slide 13: Comparison: Typical Operating Proposal vs. CFI Proposal

## Slide 14: For detailed information about CFI JELF proposal development: http://www.rso.ualberta.ca/Applying/SponsorsPrograms/CFI/JELF.aspx

## Slide 15: Proposal Development Process: “Typical” (operating) Grant
Budget
Research Plan
Institutional Alignment
Future Benefits

## Slide 16: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 17: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 18: Space Modifications: CFI Process From a Planning Perspective
Identify
Space
Equipment
Specifications
Is the Space
Appropriate?
NO
Site Review &
Scope of Work
YES
Concept Drawings
Project Timelines
Cost Estimate
Final Estimate for Proposal

## Slide 19: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 20
The CFI considers the Fair Market Value (eligible cost) of an item to be the price of the item after normal and/or educational discounts
  Normal discount: A discount a supplier would normally apply to anybody
  Educational discount: A discount offered to an institution due to its educational status.
  Eligible in-kind contribution: A non-monetary resource offered as a contribution toward a CFI-funded project. The eligible in-kind contribution is equal to the fair market value of the item less the net selling price (if any). Must be over and above Normal and Educational Discounts
* Ref: Section 6.5 (page 45) in CFI’s Policy and Procedure Guide, 2013
Budget Development In-kind Contributions

## Slide 21
Important notes about in-kind contribution:
      No in-kind provided on renovations
      Vendors are not required to offer normal or educational discounts
      May ask for an in-kind contribution from suppliers but do not ask for a specific amount or percentage*
  *https://www.innovation.ca/sites/default/files/vpupdate/cfi-vp-update-july-2016.pdf
  *https://www.innovation.ca/sites/default/files/Funds/documents/Competitivie%20bid%20process%20and%20examples_updated%20April%207_2014_EN%20-%20CSV2.pdf
Budget Development In-kind Contributions

## Slide 22: https://www.innovation.ca/sites/default/files/vpupdate/cfi-vp-update-july-2016.pdf
Budget Development In-kind Contributions

## Slide 23
  *https://www.innovation.ca/sites/default/files/Funds/documents/Competitivie%20bid%20process%20and%20examples_updated%20April%207_2014_EN%20-%20CSV2.pdf
Budget Development In-kind Contributions

## Slide 24: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 25: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits
IMPORTANT:
If you are working on a CFI proposal with a collaborator from another institution, even if UofA is not the lead you must contact you Department, Faculty and RSO as soon as possible.

## Slide 26: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 27: Proposal Development Process: CFI Projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 28: www.rso.ualberta.ca/Applying/SponsorsPrograms/CFI/OM.aspx

## Slide 29: Infrastructure Operating Funds (IOF)
Additional funds provided for direct, incremental operating expenditures
    Salaries, training, extended warranties, maintenance/repairs, replacement parts, supplies, services to support infrastructure
Researchers can access to up to 25% of finalized CFI award amount
    e.g., $1M TPC = $400K CFI = $100K IOF
Not a competition; researcher sends request to RSO to open IOF project

## Slide 30: Proposal Development Process: CFI projects
Space and Equipment Plan
Infrastructure Budget
Research Plan
O&M and Sustainability Plan
Institutional Alignment
CFI Proposal
Future Benefits

## Slide 31
UofA “Suite” of Proposals
strategic decisions
coordinated request
maximized envelope
Institutional Submission Requirements

## Slide 32: CFI Proposal Development: Communications
CFI Liaison
Contracts Specialists
Assistant Director
VP Facilities & Operations
VP Research
Director
CFI Coordinator
Space Planners
Estimators
Faculties
Departments
Dean
Writers
Chair
Researcher (Project Lead)
Co-PIs
ADR
VP Academic
Collaborating Institutions
RSO
F&O
PMO
External

## Slide 33: Post-Award Activities

## Slide 34
Competitive Bid:
SMS/PI develop and evaluate Request For Proposal (RFP)
SMS provides proposal responses to RSO
PI edits, updates and approves PR
RSO reviews and approves PR
SMS proceeds with the award and contract execution
SMS issues PO
PI
RSO
SMS
RSO
SMS
PI and/or Support administrator
PI and/or Support administrator
Attaches CFI quote
Identifies CFI line item
Creates PR for bid RSO
Reviews PR
Approves PR for bid
https://policiesonline.ualberta.ca/PoliciesProcedures/Procedures/Competitive-Bid-Procedure.pdf

## Slide 35: Expenditure Monitoring
Projects expenses for quarterly periods are downloaded from eTRAC
F18 Q1 Q2 Q3 Q4
Excel spreadsheets are sent to the PI for review
Confirm expenses
Add missing line numbers
CFI policy guidelines eligibility
Erroneous charges
Budget variances
Line item numbers
e-TRAC Download
Line item Identification
Eligibility Review
Issues Resolution

## Slide 36: Annual Reporting
PI/RSO
Purchasing documents
Construction cost update
Deadline May 5
Annual summary
Confirm Lab Space
Review Document Retention Policy
Provide Outcomes Report
CFI financial report submitted
Internal deadline May 31, 2017
CFI financial report online
CFI financial report sent to PI
Review expenditures to date
Forecast remaining amount
end date extensions
variances
new items
e-TRAC Download
Line item Identification and eligibility
Forecast and Confirmations
RSO Review and Consolidation

## Slide 37: Annual Reporting
PI/RSO
Purchasing documents
Construction cost update
Deadline May 5
Annual summary
Confirm Lab Space
Review Document Retention Policy
Provide Outcomes Report
CFI financial report submitted
Internal deadline May 31, 2017
CFI financial report online
CFI financial report sent to PI
Review expenditures to date
Forecast remaining amount
end date extensions
variances
new items
e-TRAC Download
Line item Identification and eligibility
Forecast and Confirmations
RSO Review and Consolidation

## Slide 38
Current CFI Portfolio at UofA | Number of Projects
Active Projects (infrastructure) | 58
Active Projects (IOF) | 106
Pending Projects (IOF) | 80
Award Finalizations | 17
Submitted (Pending) Projects | 28
Applications in development | 14
CFI Annual Reports due | 41
CFI Final Reports due | 16
CFI Project Progress Reports due | 95
IOF Annual Reports due | 107

## Slide 39: Lessons Learned from CFI Reviewer comments

## Slide 40
Proposals are reviewed by minimum of two expert reviewers
If necessary, the CFI:
  Seeks input from one (or more) additional expert reviewers
  And/or seeks input from the JELF Advisory Committee
The CFI’s Board of Directors makes the final funding decision
NOTE: Review process is more involved for bigger competitions
The CFI’s Review Process for JELF Proposals
(for JELF-Unaffiliated Stream, CFI request <$400K)

## Slide 41
Outcome: Oct 2013 to June 2016 UofA JELF Submissions
CFI:
  Unaffiliated Stream (<$400K CFI request): 50/61 awarded (82% success rate)
  Unaffiliated Stream (>$400K CFI request): 2/4 awarded
  Partnerships Stream: 4/4 awarded
Alberta Ministry of Economic Development and Trade:
  EDT-SEG Match to Unaffiliated JELF Applications (<$400K CFI request): 31/33 awarded (94% success rate)
    17 applications pending
    11 applications withdrawn
  EDT-SEG matches to Unaffiliated JELF Applications (>$400K CFI request): 2/2 awarded, 2 withdrawn
  EDT-SEG matches to Partnerships JELF Applications: 4/4 awarded

## Slide 42
CFI Reviewer Concerns
(JELF submissions Oct. 2013 to June 2016)
Research or Technology Development
Researchers
Need for Infrastructure
Training of HQP
Benefits to Canadians
Sustainability
All Submitted
Proposals
(n=60)
%
Chart: 
| Research plan not sufficiently detailed | Research plan not feasible | Research is not innovative | Applicants lack expertise | Equipment item justification | HQP Training Plan | Benefits to Canadians | Institutional Commitments | Operations and Maintenance Plan
At Least One Reviewer Comment | 48.3333 | 18.3333 | 26.6667 | 20 | 31.6667 | 21.6667 | 38.3333 | 13.3333 | 13.3333
Majority of Reviewers Comment | 23.3333 | 6.6667 | 3.3333 | 10 | 6.6667 | 6.6667 | 13.3333 | 0 | 3.3333
Note:
14/60 proposals assessed by third reviewer (23.3%)
4/60 assessed by JELF-AC (6.7%)

## Slide 43
CFI Reviewer Concerns
(JELF submissions Oct. 2013 to June 2016)
Research or Technology Development
Researchers
Need for Infrastructure
Training of HQP
Benefits to Canadians
Sustainability
Rejected/Partially Funded Applications
(n=12)
%
Chart: 
| Research plan not sufficiently detailed | Research plan not feasible | Research is not innovative | Applicants lack expertise | Equipment item justification | HQP Training Plan | Benefits to Canadians | Institutional Commitments | Operations and Maintenance Plan
At Least One Reviewer Comment | 91.6667 | 41.6667 | 33.3333 | 41.6667 | 41.6667 | 41.6667 | 66.6667 | 16.6667 | 25
Majority of Reviewers Comment | 75 | 25 | 8.3333 | 33.3333 | 16.6667 | 33.3333 | 50 | 0 | 8.3333
Note:
6/12 proposals assessed by third reviewer (50%)
2/12 assessed by JELF-AC (16.7%)

## Slide 44
Quality of the science and the team must be of the highest level
Research (science) must be presented as the priority
Infrastructure request should be logical means for enabling the research
Feedback from Reviewer Comments

## Slide 45
Feedback from Reviewer Comments
The innovative nature of the project is crucial
  “Novel” ≠ “innovative”
  Proposal should represent “new way of doing things”
  Interdisciplinary and integrative research is particularly innovative

## Slide 46
Ability to deliver on the project (feasibility) is crucial
Methods in the research plan must be scientifically sound
Reviewers must be convinced that research plan can be ‘pulled off’
Feedback from Reviewer Comments

## Slide 47
Feedback from Reviewer Comments
Clearly outlined objectives, goals and methods will demonstrate to expert reviewers that research plan is sound
Final funding decisions are made by non-expert reviewers
  All concepts should be fully explained in near-lay terms
  Explain all acronyms to avoid jargon
Background information should substantiate feasibility of research approach
  Use supporting/preliminary data to substantiate claims
  Proposal should stand on its own
  References ≠ bibliography
  Grantsmanship!!

## Slide 48
Collaborations are vital
  Not necessarily co-PIs
  Strong collaborations may help alleviate concern that applicants have insufficient expertise
  Avoid describing tentative collaborations
Need for Infrastructure must justify both:
  Why the selected equipment is the right equipment for the project
  Need for the equipment in relation to equipment that is already available
    Applicants should address both what is already available and what has been requested in pending CFI applications submitted throughout institution
A clearly outlined plan for training HQP is important
  Specify how trainees would be involved in the research plan
  How many trainees?
Feedback from Reviewer Comments

## Slide 49
Benefits to Canadians should be specific
  For basic scientific research: describe anticipated benefits
    e.g. new treatments if the research is successful
    how would results be exploited if project is successful?
  For applied/translational research: a detailed knowledge mobilization/technology transfer plan is critical
Reviewers expect to see a well-considered plan for potential operations and maintenance requirements
Feedback from Reviewer Comments